PARTNER MEETING 2

Value-Behaviour Dynamics in Garment Lifecycles

Sprint 1 Review Meeting, March 17, 2026

TABLE OF CONTENTS

Executive Summary	1

Key Insights	2

Prototype Development	2

Pivot Moment: Person vs. Garment Focus	2

Framework and Methodology Insights	2

Decisions and Conclusions	3

Timeline Context	3

Key Reminders	3

# Executive Summary

The second partner meeting served as the Sprint 1 review, where the team presented their research findings, prototype development, and overall progress update to the partner Francesco and MariLuz.

The team’s central conclusion from Sprint 1 is that the core challenge is not about producing data or changing behaviour, but about designing a research tool that simultaneously collects garment-lifecycle data for researchers and delivers genuine value to participants. This dual-value assumption has driven all prototype development.

However, a key misalignment was identified: the team had focused their research tools on classifying user personas and behavioural archetypes, whereas the partner’s core research objective centres on understanding the usage patterns of different garment types over time. Francesco redirected the focus from “what kind of person are you?” to “what kind of garment are you describing and how does it move through its lifecycle?”

The meeting concluded with concrete agreements on reframing the survey approach, narrowing garment categories to four archetypes (work/formal, leisure/sport, special occasion, idle), and establishing a fast feedback loop on revised survey questions before Sprint 2 data collection begins.

# Key Insights

## Prototype Development

- Two tools were developed: (1) a board-game conversational object assigning “wardrobe archetypes” based on answers, and (2) a scenario-based decision tree app simulating garment lifecycle events.

- The decision tree app (third iteration) received positive feedback on design quality and data export capability (CSV/JSON). Usability testing scored well across participants.

- Users preferred narrative and scenario-based formats over traditional survey approaches.

- Key usability issues included swipe gesture challenges across devices and insufficient clarity in terminology (e.g., “emotional connection” was not intuitive for end users).

## Pivot Moment: Person vs. Garment Focus

- Francesco Partner identified the central misalignment: the current tools focus on categorising the person (user archetypes/personas), while the research objective is to understand usage patterns of different garment types over their lifecycle.

- The research subject should be the garment, not the individual. The question is “how does a garment move through its lifecycle?” rather than “what type of consumer am I?”

- MariLuz noted that persona/archetype outputs still hold engagement value (the “Tarot effect”), but Francesco suggested reframing this as “a Tarot of your wardrobe,” telling users something about their garments rather than about themselves.

- Price and monetary value of the garment was flagged as a fundamental variable that shapes care, repair, and disposal decisions; it must be included as a survey question.

## Framework and Methods Insights

- The decision tree visualisation was praised as a strong basis for a research framework that maps how garments transition between usage categories over time.

For each garment archetype, distinct research questions emerge. Idle items raise questions about reactivation; special occasion garments prompt inquiry into increasing frequency of use; daily and sport wear focus on extending lifetime through care and repair.

- Question design was acknowledged as a critical skill. Poorly phrased questions yield unreliable data, and Francesco stressed the importance of validating questions before deployment.

# Decisions and Conclusions

- Shift the research lens from person-centred archetypes to garment-centred lifecycle analysis. The primary unit of study is the garment, not the user.

- Adopt four garment archetypes as the classification framework: work/formal, leisure/sport, special occasion, and idle (inactive) garments.

- Consider splitting the survey into up to four separate questionnaires (one per garment archetype) to avoid respondent fatigue, each sent to different participants.

- Include mandatory baseline data points in the survey: garment type, approximate age, frequency of use, and approximate purchase price.

- Add at least one question each on care practices and repair behaviour (including use of professional services).

- Allow multiple-answer selections where appropriate, as single-choice formats were found to frustrate respondents.

- Provide concrete definitions and examples for vague answer options (e.g., “sometimes” should specify “about once per month”).

- Retain the current visual design and data export functionality of the decision tree app; the design is considered production-ready.

- Begin documenting the reasoning behind the research framework as groundwork for the Sprint 4 deliverable (publication/knowledge handover document).

# Timeline Context

| Sprint | Status | Key Notes |
| --- | --- | --- |
| Sprint 2 | In Progress | Balance insight refinement with scaling data collection. |
| Sprint 4 | Upcoming | Final intimate review with partner (Francesco). Deadline for publication/knowledge handover document. |
| Sprint 5 | Upcoming | Public showcase event (larger, less focused setting). All deliverables must be finalised beforehand. |

### Key Reminders

- MariLuz warned against over-refining prototypes at the expense of collecting real data. The team should finalise questions quickly and shift to fieldwork.

- Survey questions should be shared with Francesco for validation before Sprint 2 data collection begins.